## KT Topics
jBPM KT on WildFly Environment
Environment | KT session topics | Planned Date | KT With | Date | KT Status | Dev Task | Documentation References | ABM SVN References
JBPM and KIE WB | JBPM architecture overview | 2019-02-20 | shyam, Deepak, Sumit | 2019-02-21 | Done | Go through Reference Guide or Tutorial | jBPM API & Documentation https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#d0e86 https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#d0e2061
| KIE-WB installation and configuration on WildFly server | 2019-02-20 | shyam, Deepak, Sumit | 2019-02-21 | Done | Setup and Configure in Local Dev Machine | https://docs.jboss.org/author/display/WFLY10/add-user+utility https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#jBPMPersistence | https://192.168.100.7/svn/ABM_SAAS_Product/trunk/jbpmplatform/baseversion/ https://192.168.100.7/svn/ABM_SAAS_Product/trunk/jbpmplatform/baseversion/README.html
| jBPM process component which we are using. | 2019-02-21 | Deepak, Sumit | 2019-02-25 | Done | Go through Reference Guide or Tutorial | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#jBPMBPMN2
| Process modeling | 2019-02-21 | Deepak, Sumit | 2019-02-25 | Done | Go through Reference Guide or Tutorial | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#jBPMBPMN2
| Data model creation | 2019-02-21 | Deepak, Sumit | 2019-02-25 | Done | Go through Reference Guide or Tutorial | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#wb.QuickStartDefineDataModel
| KIE User Roles in details |  | Deepak, Sumit | 2019-02-25 | Done | Go through Reference Guide or Tutorial | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#wb.Roles https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#remote.rest.permissions
| KIE Tables and Column in details |  | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-11 | Done | Go through Reference Guide or Tutorial
BPM Processes business logic and configuration | scrutiny | 2019-02-22 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-04 | Done |  |  | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BPMS_Process/198
| maker-checker | 2019-02-22 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-05 | Done
| works-management | 2019-03-04 | shyam, Deepak, Sumit | 2019-03-15 | Done
| property | 2019-03-04 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-08 | Done
| rti | 2019-03-05
| care | 2019-03-05 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-15 | Done
| Auto escalation |  | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-15 | Done
| Multiple approval |  | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-15 | WIP
JBPM and KIE WB | KIE project creation/management | 2019-03-06 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-02-26 | Done
| KIE project structure | 2019-03-06 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-02-26 | Done
| KIE project dependencies | 2019-03-06 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-02-26 | Done
| KIE project deployments | 2019-03-06 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-02-26 | Done
| Runtime services | 2019-03-07 | shyam, Deepak, Jeetendra,Aarti | 2019-03-14 | Done
| Process internal API | 2019-03-07 | shyam, Deepak, Jeetendra,Aarti | 2019-03-14 | Done | Go through all processes and their internal scripts
| Task API | 2019-03-08 | shyam, Deepak, Jeetendra,Aarti | 2019-03-14 | Done
| Dynamic task assignment | 2019-03-08 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-04 | Done |  |  | http://192.168.100.198:8090/mainetbpmservice/services/rest/api-docs?url=/mainetbpmservice/services/rest/swagger.json#/Task%20Assignment%20Service
MainetBpmService | Project overview. | 2019-03-11 | shyam, Deepak, Sumit | 2019-03-07 | Done
| project installation and configuration on WildFly server | 2019-03-11
| KIE integration using Java remote API | 2019-03-12 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-12 | Done |  | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#jBPMRemoteAPI
| Dynamic process deployment selection | 2019-03-12 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-07 | WIP
| Common workflow parameter | 2019-03-12 | shyam, Deepak, Sumit | 2019-03-07 | Done
| Common BPM services | 2019-03-13
| Workflow transition data services | 2019-03-13 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-11 | Done
| CXF and swagger Configuration | 2019-03-13 | shyam, Deepak, Jeetendra,Aarti | 2019-03-18 | Done
MainetService | Workflow Master configuration | 2019-04-14 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-05 | Done | Try to configure new workflow in workflow master |  | http://192.168.100.157:8090/MainetService/
| Entitlement Configuration | 2019-04-14 | shyam, Deepak, Sumit | 2019-03-08 | Done
| Workflow type identification | 2019-04-14 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-07 | Done
| Workflow parameter | 2019-04-14 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-08 | Done
| Workflow execution services | 2019-04-14 | shyam, Deepak, Sumit, Jeetendra | 2019-03-08 | Done
| Workflow task assignment services | 2019-05-18 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-12 | Done |  |  | http://192.168.100.198:8090/mainetbpmservice/services/rest/api-docs?url=/mainetbpmservice/services/rest/swagger.json#/Task%20Assignment%20Service
| Workflow task notification services | 2019-05-19 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-12 | Done |  |  | http://192.168.100.157:8090/MainetService/services/rest/common/api-docs?url=/MainetService/services/rest/common/swagger.json#/Task%20Notification%20Service/notifyUser
| BPM process deployment master | 2019-05-19 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-13 | Done
Build and deployment | Daily build and deployment process |  | shyam, Deepak, Jeetendra,Aarti | 2019-03-13 | Done | Go through Reference Guide or Tutorial
| BPM process deployment |  | shyam, Deepak, Jeetendra,Aarti | 2019-03-13 | Done | Go through Reference Guide or Tutorial
| Rules deployment |  | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-18 | Done
Rules | Drools Setup & Configuration |  | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-18 | Done
| Drools Process and API Guidelines |  | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-18 | Done

## Build and deployment
Process ManiettBpmService Environment | IP:PORT | Build Type | Build Owner | SVN SRC URL | SVN TAG URL | BPM Process GIT Repository
Dev | http://192.168.100.198:8090 | Jenkins | Rohit Thorse KT Team | https://192.168.100.7/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetbpmservice | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/dev/mainetbpmservice | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BPMS_Process/198
Test | http://192.168.100.243:8090 | Jenkins | Sam & Diwakar | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/dev/mainetbpmservice | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/sit/mainetbpmbrms | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BPMS_Process/243
Cloud | http://182.18.168.246:8100/ | Manual | Sam & Diwakar | NA | NA | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BPMS_Process/246
Prod | NA | Manual | Sam & Diwakar | NA | NA | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BPMS_Process/Production
Rules and ManiettBpmService Environment | IP:PORT | Build Type | Build Owner | SVN SRC URL | SVN TAG URL | Rules GIT Repository | Updated Rules Sheet
Dev | http://192.168.100.198:8090 | Jenkins | Rohit Thorse Amruta Mane | https://192.168.100.7/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetbpmservice | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/dev/mainetbpmservice | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BRMS_Rules/198 | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/BRMS
Test | http://192.168.100.243:8090 | Jenkins | Sam & Diwakar Amruta Mane | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/dev/mainetbpmservice | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/sit/mainetbpmbrms | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BRMS_Rules/243 | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/BRMS
Cloud | http://182.18.168.246:8100/ | Manual | Sam & Diwakar Amruta Mane | NA | NA | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BRMS_Rules/246 | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/BRMS
Prod | NA | Manual | Sam & Diwakar Amruta Mane | NA | NA | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BRMS_Rules/Production | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/BRMS
ManietService Environment | IP:PORT | Build Type | Build Owner | SVN SRC URL | SVN TAG URL
Dev | http://192.168.100.157:8090 | Jenkins | Rohit Thorse | https://192.168.100.7/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetservice | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/dev/mainetservice
Test | http://192.168.100.230:8080/ | Jenkins | Sam & Diwakar | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/dev/mainetservice | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/sit/mainetservice
Cloud | http://182.18.168.246 | Manual | Sam & Diwakar | NA | NA
Prod | NA | Manual | Sam & Diwakar | NA | NA
ManietPortal Environment | IP:PORT | Build Type | Build Owner | SVN SRC URL | SVN TAG URL
Dev | http://192.168.100.157:8090 | Jenkins | Rohit Thorse | https://192.168.100.7/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetportal | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/dev/mainetportal
Test | http://192.168.100.230:8080/ | Jenkins | Sam & Diwakar | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/dev/mainetportal | https://192.168.100.7/svn/ABM_SAAS_Product/tags/mainetproduct/sit/mainetportal
Cloud | http://182.18.168.246 | Manual | Sam & Diwakar | NA | NA
Prod | NA | Manual | Sam & Diwakar | NA | NA

## S4 (hidden)
Build and deployment For Rules | Drools Setup & Configuration
Drools Process and API Guidelines
Build and deployment Server Details | Rules Environment 1. Local - Server(), SVN URI(), OWNER() 2. QA - Server(), SVN URI(), OWNER() 3. Production - Server(), SVN URI(),OWNER() | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BRMS_Rules
Build and deployment Server Details | jBPM Environment 1. Local - Server(), SVN URI(), OWNER() 2. QA - Server(), SVN URI(), OWNER() 3. Production - Server(), SVN URI(),OWNER() | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BPMS_Process
Build and deployment Server Details | Mainet Service(BRMS Middleware) Environment 1. Local - Server(), SVN URI(), OWNER() 2. QA - Server(), SVN URI(), OWNER() 3. Production - Server(), SVN URI(),OWNER() | https://abmsvn.swastik.abmindia.com/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetbpmservice
Build and deployment Server Details | Mainet Service Environment 1. Local - Server(), SVN URI(), OWNER() 2. QA - Server(), SVN URI(), OWNER() 3. Production - Server(), SVN URI(),OWNER() | https://abmsvn.swastik.abmindia.com/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetservice https://abmsvn.swastik.abmindia.com/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetportal