## jBPM
jBPM KT on WildFly Environment
Environment | KT session topics | Planned Date | KT With | Date | KT Status | Dev Task | URI References | ABM SVN References
JBPM and KIE WB | JBPM architecture overview | 2019-02-20 | shyam, Deepak, Sumit | 2019-02-21 | Done | GUIDE | jBPM API & Documentation https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#d0e86 https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#d0e2061
| KIE-WorkBench installation and configuration on WildFly server BPM Service(Middleware) Setup & Configuration | 2019-02-20 | shyam, Deepak, Sumit | 2019-02-21 | Done | Setup and Configure | https://docs.jboss.org/author/display/WFLY10/add-user+utility https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#jBPMPersistence | https://192.168.100.7/svn/ABM_SAAS_Product/trunk/jbpmplatform/baseversion/ https://192.168.100.7/svn/ABM_SAAS_Product/trunk/jbpmplatform/baseversion/README.html
| jBPM process component which we are using. | 2019-02-21 | Deepak, Sumit | 2019-02-25 | Done | GUIDE | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#jBPMBPMN2
| Process modeling | 2019-02-21 | Deepak, Sumit | 2019-02-25 | Done | GUIDE | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#jBPMBPMN2
| Data model creation | 2019-02-21 | Deepak, Sumit | 2019-02-25 | Done | GUIDE | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#wb.QuickStartDefineDataModel
| KIE User Roles in details |  | Deepak, Sumit | 2019-02-25 | Done | GUIDE | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#wb.Roles https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#remote.rest.permissions
| KIE Tables and Column in details |  | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-11 | Done | GUIDE | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#jBPMPersistence
BPM Processes business logic and configuration | scrutiny | 2019-02-22 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-04 | Done |  |  | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BPMS_Process/198
| maker-checker | 2019-02-22 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-05 | Done
| works-management | 2019-03-04 | shyam, Deepak, Sumit
| property | 2019-03-04 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-08 | Done
| rti | 2019-03-05
| care | 2019-03-05
Auto escalation
Multiple approval
JBPM and KIE WB | KIE project creation/management | 2019-03-06 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-02-26 | Done
| KIE project structure | 2019-03-06 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-02-26 | Done
| KIE project dependencies | 2019-03-06 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-02-26 | Done
| KIE project deployments | 2019-03-06 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-02-26 | Done
| Runtime services | 2019-03-07 | shyam, Deepak, Jeetendra,Aarti | 2019-03-14 | WIP
| Process internal API | 2019-03-07 | shyam, Deepak, Jeetendra,Aarti | 2019-03-14 | Done | Go through all processes and their internal scripts
| Task API | 2019-03-08 | shyam, Deepak, Jeetendra,Aarti | 2019-03-14 | WIP
| Dynamic task assignment | 2019-03-08 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-04 | Done |  |  | http://192.168.100.198:8090/mainetbpmservice/services/rest/api-docs?url=/mainetbpmservice/services/rest/swagger.json#/Task%20Assignment%20Service
MainetBpmService | Project overview. | 2019-03-11 | shyam, Deepak, Sumit | 2019-03-07 | Done
| project installation and configuration on WildFly server | 2019-03-11
| KIE integration using Java remote API | 2019-03-12 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-12 | Done |  | https://docs.jboss.org/jbpm/release/6.5.0.Final/jbpm-docs/html_single/#jBPMRemoteAPI
| Dynamic process deployment selection | 2019-03-12 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-07 | WIP
| Common workflow parameter | 2019-03-12 | shyam, Deepak, Sumit | 2019-03-07 | Done
| Common BPM services | 2019-03-13
| Workflow transition data services | 2019-03-13 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-11 | Done
| CXF and swagger Configuration | 2019-03-13
MainetService | Workflow Master configuration | 2019-04-14 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-05 | Done | Try to configure new workflow in workflow master |  | http://192.168.100.157:8090/MainetService/
| Entitlement Configuration | 2019-04-14 | shyam, Deepak, Sumit | 2019-03-08 | Done
| Workflow type identification | 2019-04-14 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-07 | Done
| Workflow parameter | 2019-04-14 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-08 | Done
| Workflow execution services | 2019-04-14 | shyam, Deepak, Sumit, Jeetendra | 2019-03-08 | Done
| Workflow task assignment services | 2019-05-18 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-12 | Done |  |  | http://192.168.100.198:8090/mainetbpmservice/services/rest/api-docs?url=/mainetbpmservice/services/rest/swagger.json#/Task%20Assignment%20Service
| Workflow task notification services | 2019-05-19 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-12 | Done |  |  | http://192.168.100.157:8090/MainetService/services/rest/common/api-docs?url=/MainetService/services/rest/common/swagger.json#/Task%20Notification%20Service/notifyUser
| BPM process deployment master | 2019-05-19 | shyam, Deepak, Sumit,Jeetendra,Aarti | 2019-03-13 | Done
Build and deployment For BPM | Daily build and deployment process |  | shyam, Deepak, Jeetendra,Aarti | 2019-03-13 | Done | GUIDE
| BPM process deployment |  | shyam, Deepak, Jeetendra,Aarti | 2019-03-13 | Done | GUIDE
Build and deployment For Rules | Drools Setup & Configuration
Drools Process and API Guidelines
Build and deployment Server Details | Rules Environment 1. Local - Server(), SVN URI(), OWNER() 2. QA - Server(), SVN URI(), OWNER() 3. Production - Server(), SVN URI(),OWNER() | [6 empty] | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BRMS_Rules
Build and deployment Server Details | jBPM Environment 1. Local - Server(), SVN URI(), OWNER() 2. QA - Server(), SVN URI(), OWNER() 3. Production - Server(), SVN URI(),OWNER() | [6 empty] | https://192.168.100.7/svn/ABM_SAAS_Product/branches/projects/suda/documents/releases/release_documents/BPMS_Process
Build and deployment Server Details | Mainet Service(BRMS Middleware) Environment 1. Local - Server(), SVN URI(), OWNER() 2. QA - Server(), SVN URI(), OWNER() 3. Production - Server(), SVN URI(),OWNER() | [6 empty] | https://abmsvn.swastik.abmindia.com/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetbpmservice
Build and deployment Server Details | Mainet Service Environment 1. Local - Server(), SVN URI(), OWNER() 2. QA - Server(), SVN URI(), OWNER() 3. Production - Server(), SVN URI(),OWNER() | [6 empty] | https://abmsvn.swastik.abmindia.com/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetservice https://abmsvn.swastik.abmindia.com/svn/ABM_SAAS_Product/branches/mainetproductmain/mainetportal